## Delivery Forecast
ETS 2702 solution delivery forecast
Five parallel teams. Three completed Must stories across the release; one each in Teams 1–3.
Release metric | Calculated result | Definition
Solution teams | 5 | Each owns 1 linked component epic
Team members | 25 | 5 members per team
Nominal aggregate velocity | 50 | Points/week; team-level forecasts govern
Unique release stories | 25 | Shared solution/component scope
Release scope, points | 75 | 3 points per FR / linked story
Completed spillover stories | 3 | Release-wide total, not per team
Completed points | 9 | Done includes Must automation
Remaining full scope, points | 66 | Remaining scope across teams
Remaining Must scope, points | 51 | Must gaps across teams
Release completion | 12% | Done / total release points
Must completion | 15% | Done Must / total Must requirements
Must team-work forecast, weeks | 2 | Latest required team finish
Full team-work forecast, weeks | 2 | Latest required team finish
Full whole-story plan, weeks | 2 | Whole stories within weekly point limit
Release-ready forecast, weeks | Unestimated | Team finish + confirmed sequential gate weeks
Input | Value | Definition
Points per story / FR | 3 | One FR maps to one shared story
Tasks per story | 10 | Included in story estimate
Sequential release-gate weeks |  | Blank = unestimated; 0 = confirmed no extra work
Scenario velocity/team | Aggregate velocity | Must point weeks | Full point weeks | Full story weeks
7 | 35 | 2 | 3 | 3
10 | 50 | 2 | 2 | 2
13 | 65 | 1 | 2 | 2
Forecast starts at the next planning point; no calendar start date or release deadline was supplied.
Default scenario assumes independent ready work. Estimate dependencies and extra solution gates before setting readiness.

## Solution Teams
Solution team scope and finish forecast
Amber fields are editable. Each row is one solution epic and its linked component epic. Done spillover is Must.
Solution / component | Members | Velocity / week | Stories / FRs | Must FRs | Done stories | Done Must | Total points | Done points | Full remaining | Must remaining | Must weeks | Full weeks | Full story weeks | Completion
SOL-1 / CMP-1 | 5 | 10 | 5 | 4 | 1 | 1 | 15 | 3 | 12 | 9 | 1 | 2 | 2 | 20%
SOL-2 / CMP-2 | 5 | 10 | 5 | 4 | 1 | 1 | 15 | 3 | 12 | 9 | 1 | 2 | 2 | 20%
SOL-3 / CMP-3 | 5 | 10 | 5 | 4 | 1 | 1 | 15 | 3 | 12 | 9 | 1 | 2 | 2 | 20%
SOL-4 / CMP-4 | 5 | 10 | 5 | 4 | 0 | 0 | 15 | 0 | 15 | 12 | 2 | 2 | 2 | 0%
SOL-5 / CMP-5 | 5 | 10 | 5 | 4 | 0 | 0 | 15 | 0 | 15 | 12 | 2 | 2 | 2 | 0%
Do not multiply points by member count. Use actual availability separately; story points are not person-hours.

## Parallel Plan
ETS 2702 two-week parallel plan
Illustrative baseline plan. Replace planned story counts when team scope or velocity changes; actuals remain blank.
Team | Week 1 Must | Week 1 points | Week 2 Must | Week 2 Should | Week 2 points | Original committed pts | Original scope Done pts | Added Done pts | Actual velocity | Commitment completion
Team 1 | 3 | 9 | 0 | 1 | 3 |  |  |  | n.a. | n.a.
Team 2 | 3 | 9 | 0 | 1 | 3 |  |  |  | n.a. | n.a.
Team 3 | 3 | 9 | 0 | 1 | 3 |  |  |  | n.a. | n.a.
Team 4 | 3 | 9 | 1 | 1 | 6 |  |  |  | n.a. | n.a.
Team 5 | 3 | 9 | 1 | 1 | 6 |  |  |  | n.a. | n.a.
Release plan totals | 15 | 45 | 2 | 5 | 21
Checkpoint | Done release points | Remaining points | Done Must FRs
Baseline | 9 | 66 | 3
After week 1 | 54 | 21 | 18
After week 2 | 75 | 0 | 20
Enter original sprint commitment and Done points for one common reporting week. Added Done work affects velocity only.
Aggregate commitment completion | Result
n.a.