## Forecast
ETS 2702 Scrum Master forecast
One team of 5 covers all components. Shared solution/component stories; 3 completed spillover stories are Must.
Release metric | Result | Interpretation
Release stories | 25 | 25 unique stories
Release points | 75 | All story work included in 3 points
Must stories | 20 | 4 per component epic
Must points | 60 | Automation included in Definition of Done
Completed stories | 3 | Already completed spillover
Completed points | 9 | Do not subtract twice
Remaining release points | 66 | Full scope remaining
Remaining Must points | 51 | Assumes completed Must IDs as shown
Release completion | 12% | Done points / total scope
Must completion | 15% | Done Must points / total Must scope
Whole stories / sprint | 3 | When velocity is used as weekly planning limit
Must point forecast (weeks) | 6 | Remaining points / average velocity
Full point forecast (weeks) | 7 | Can require a 12-point sprint
Must whole-story plan (weeks) | 6 | No partial story credit
Full whole-story plan (weeks) | 8 | Conservative fixed weekly planning limit
Remaining verification tasks | 220 | Work items, not extra story points
Remaining Must automation tasks | 170 | Done Must stories already include automation
Planning input | Value | Definition
Team members | 5 | One team, not five teams
Team velocity, points/week | 10 | Reference historical average
Points per story / FR | 3 | One FR maps to one story
Testable tasks per story | 10 | Included in the story estimate
Scenario velocity | Must point weeks | Full point weeks | Whole stories/week | Must story weeks | Full story weeks
7 | 8 | 10 | 2 | 9 | 11
10 | 6 | 7 | 3 | 6 | 8
13 | 4 | 6 | 4 | 5 | 6
Scenarios are illustrative, not confidence intervals. Forecast weeks start from the next planning point.

## Components
ETS 2702 component delivery scope
Completed Must examples: US-01, US-02 in CMP-1 and US-06 in CMP-2. Amber fields are editable.
Component epic | Total stories | Must stories | Done stories | Done Must stories | Total points | Done points | Remaining points | Remaining Must points | Completion | Input check
CMP-1 Registration | 5 | 4 | 2 | 2 | 15 | 6 | 9 | 6 | 40% | OK
CMP-2 Session Management | 5 | 4 | 1 | 1 | 15 | 3 | 12 | 9 | 20% | OK
CMP-3 Mobility | 5 | 4 | 0 | 0 | 15 | 0 | 15 | 12 | 0% | OK
CMP-4 Paging | 5 | 4 | 0 | 0 | 15 | 0 | 15 | 12 | 0% | OK
CMP-5 Monitoring | 5 | 4 | 0 | 0 | 15 | 0 | 15 | 12 | 0% | OK
Must counts must not exceed scope; Done Must must not exceed either Done or Must.
Input consistency | Result
Review row limits too

## Sprint Tracker
Weekly sprint delivery tracker
The plan is illustrative; actual sprint fields are blank until supplied. Points count only when a story becomes Done.
Week | Plan Must stories | Plan Should stories | Plan points | Cumulative planned Done | Planned remaining | Original commitment pts | Original scope Done pts | Added work Done pts | Actual velocity | Commitment completion | Original spillover pts | Goal achieved?
1 | 3 | 0 | 9 | 18 | 57 |  |  |  | n.a. | n.a. | n.a.
2 | 3 | 0 | 9 | 27 | 48 |  |  |  | n.a. | n.a. | n.a.
3 | 3 | 0 | 9 | 36 | 39 |  |  |  | n.a. | n.a. | n.a.
4 | 3 | 0 | 9 | 45 | 30 |  |  |  | n.a. | n.a. | n.a.
5 | 3 | 0 | 9 | 54 | 21 |  |  |  | n.a. | n.a. | n.a.
6 | 2 | 1 | 9 | 63 | 12 |  |  |  | n.a. | n.a. | n.a.
7 | 0 | 3 | 9 | 72 | 3 |  |  |  | n.a. | n.a. | n.a.
8 | 0 | 1 | 3 | 75 | 0 |  |  |  | n.a. | n.a. | n.a.
Enter 0 for no added Done work. Original scope excludes later additions; velocity includes all work becoming Done.
Goal success rate | Completed sprints with Yes / Yes + No
n.a.